|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **ACTION INITIATIVE PLAN** | | | | | |
| **Leader:** Greg  **Team:** Deborah, Mark, Jane, LaQuanda | **Initiative:** AAB Development Committee  **Due Date**: | | | **Last Review:**  **This Review:**  10/25/2016 |  |
| **Objectives:**  To sustain sufficient funding for alumni programming initiatives.  **Key Deliverables:**   1. Launch “Giving Tuesday” Initiative 2. Rename the “ Alumni Legacy” Fund 3. Provide opportunities for Donors to give at more significant and sustaining levels – for Banquet & Summits   **Cost:**  TBD | **Action Steps** | **Today’s Status** | **Due Date** | **Cost?** | **Accountable** |
| 1. Develop project plan and timeline for “Giving Tuesday” Initiative |  | 10/29/2016 | None | Jane |
| 1. Work with Communications Manager to develop communications plan for “Giving Tuesday” Initiative |  | 11/4/2016 | None | Jamie |
| 1. Secure full support of CCSF Board of Directors for “Giving Tuesday” |  | 10/26/2016 | None | Mark |
| 1. Secure full support of Alumni Advisory Board for “Giving Tuesday” |  | 10/22/2016 | None | Greg |
| 1. Secure full support of CCSF Staff for “Giving Tuesday” |  | 10/27/2016 | None | Jane |
| 1. Evaluate results of non-merchandise “Giving Tuesday” and add year-end option, if warranted |  | 12/1/2016 | None | Greg |
| 1. Develop strategy to rename the “Alumni Legacy” Fund to better reflect intended use of donations |  | 11/4/2016 | None | Jane |
| 1. Work with Communications Manager to develop communications strategy for renamed Fund |  | 11/18/2016 | None | Jane |
| 1. Identify a portfolio of opportunities for Donors to give at more significant levels |  | 12/16/2016 | None | Greg (with Jane) |
| 1. Work with Communications Manager to develop strategy for promoting new and differentiated opportunities for Donors |  | 1/13/2017 | None | Jane |
| 1. Explore possibility of merchandise sale of bowties and scarves to coincide with 2018 Service Summit |  | 2/1/2017 | None | Jane |